## Sheet2
Sample Recruitment Work Plan
RECRUITMENT
Strategy | Action Steps | Responsibility | Budget/Resources | Timeline | Measurements | Outcome
Recruitment Goal 1: Recruit and train 90 new volunteers in FY20.
Build relationships with local TV stations in order to run PSAs. | 1) Identify stations with audiences that match our target demographic of volunteers 2) Schedule a meeting with each of the identified stations 3) Send PSA to stations willing to run it | Executive Director & Recruitment Director | Budget: $xx Resources: PSA from Texas CASA's marketing toolkit | Identify stations by Jan. 31; Schedule meetings by Feb. 15; Have PSAs running by Mar. 31 | Have xx TV stations running a CASA PSA at least xx times per week for xx months | xx TV stations agreed to run PSA xx times per week for xx months.
Host targeted small group events | 1) Identify 4 to 6 board members or advocates who can host. 2) Select dates and create a calendar of events for the year 3) Promote in newsletter, social media and face to face | Executive Director, Program Director & Recruitment Director | Budget: $xx Resources: | Identify hosts by Dec. 15; Schedule Q1 parties by Dec. 31; Host first party in Jan. | Host a minimum of four house parties per quarter | Hosted xx house parties in Q1; Hosted xx house parties in Q2; Hosted xx house parties in Q3; Hosted xx house parties in Q4
Recruitment Goal 2: Increase community partnerships
Increase number of faith-based partnerships | 1) Identify churches from all faiths and are already involved with child welfare or social impact causes. 2) Partner with DFPS faith-based specialist to identify organizations involved in the care portal or foster care 3) Utilize current volunteers to help you connect to their faith-based organizations 4) Meet with clergy from identified organizations 5) Hold information sessions at interested organizations | Executive Director, Program Director & Recruitment Director | Budget: $xx Resources: Faith-based recruitment materials from Texas CASA | Reach out to DFPS in Feb. Have organizations identified by Mar. Host at least 1 information session per month | Host a minimum of xx information sessions at faith-based organizations Secure at least xx faith-based organizations that are willing to include CASA in their missionary. | xx organizations invite CASA to speak to their members on a monthly basis
Invite current volunteers to a meeting to identify their connections to community groups & leaders. | 1) Decide on date and location 2) Create agenda 3) Send out invite & collect RSVPs 4) Secure snacks, drinks, etc. 5) Sent out event reminder email 6) Host event | Recruitment Director & Program Director | Budget: $xx Resources: office space, connection with local restaurant | Begin planning in Jan. Host event in Feb. | Have at least xx current volunteers attend and receive at least xx new contacts for community groups & leaders. | Received xx new community groups to contact and have scheduled a meeting with xx of them.
RETENTION
Strategy | Action Steps | Responsibility | Budget/Resources | Timeline | Measurements | Outcome
Retention Goal: Increase the # of active volunteers who fulfill a case commitment by xx% in FY20
Increase the number of phone calls to the volunteers by 1 per month | Create a call schedule for all volunteers actively on a case | Supervisors | Budget: $xx | Ongoing | Call at least volunteer xx times per month | Called 90% of volunteers xx times per month