| Time Frame | Project Goal | Activity | Expected Completion Date | Person Responsible |
| --- | --- | --- | --- | --- |
| Year 1 | The Infant and Toddler Team will be trained regarding the 4-5 year old client population to assist them in developing a plan to effectively serve this children The Infant and Toddler Team will begin serving children in the 4-5 age range and continue to serve the 0-3 population All CASA volunteers serving clients within the 0-5 age range will be notified of the changes to the program CASA volunteers working with 0-5 year old foster care population will receive specialized training to enhance advocacy skills Report outcomes for Infant and Toddler Project | Staff will attend trainings provided by partners and stakeholders serving the 4-5 population Caseloads will be reassigned as needed to the appropriate team members and volunteers Volunteers will be notified through the Volunteer Newsletter and face to face communications from the Infant and Toddler Team Develop specialized training and continuing education trainings for CASA volunteers working with 0-5 year old foster care population Develop outcome tracking report | January 2012 Ongoing Ongoing May 2012 Ongoing August 2012 September 2012 | CASA Program Director, Infant and Toddler Team Leader, Infant and Toddler CASA Supervisor CASA Program Director and Infant and Toddler Team CASA Program Director, Infant and Toddler Team CASA Program Director, Infant and Toddler Team, Volunteer Services Team CASA Program Director, Infant and Toddler Team |
| Year 2 | 50% of CASA volunteers serving the 0-5 foster care client population will be trained in Positive Visitation Practices Develop an in-house multi-disciplinary team for the Infant and Toddler Project Community partners will be aware of the issues youth face in foster care, specifically the 0-5 year old population | All CASA volunteers serving the 0-5 client population will be offered the Positive Visitation Practices Provide space for Early Childhood Intervention Specialist or Parent Coach at Child Advocates of Fort Bend CASA staff will provide training to the community and partner agencies in an effort to get the community to serve the children of the Infant and Toddler Project | March 2013 June 2013 August 2013 | CASA Program Director, Infant and Toddler Team, Volunteer Services Team CAFB Executive Director, CASA Program Director, Infant and Toddler Team, Financial Director CASA Program Director, Infant and Toddler Team, Volunteer Services Team |